## Slide 1: KLINK Pilot Delivery Team Update
Diego Bernini, Emanuele Panzeri, Alessio Vertemati
{d.bernini, e.panzeri, a.vertemati}@sirisacademic.com
October 15th, Barcelona

## Slide 2: Agenda
KLINK Pilot: Delivery and Deadlines
Delivery Team Methodology
Beyond the Pilot

## Slide 3: KLINK Pilot: Delivery and Deadlines

## Slide 4: Recalling the delivery approach
Developing the distributed infrastructure and basic services first, then enhanced services
Basic services:
  Basic Document Management targeted to specific users (Content Managers)
  Distributed search & retrieval where results are displayed as ordered list
Enhanced services:
  Effective presentation of results via a suitable methapor
  Personalization: favourite documents, tracking user activities => «MyKLINK»

## Slide 5: Software releases: deadlines
RELEASE | DEADLINE | FEATURES | RATIONALE
BASIC PILOT PRELIMINARY RELEASE (KLINK version 0) | NOVEMBER 15TH 2014 | 3 institutions (Camp Alatoo, State Agency, UCA) Global search only Low resiliency | Early End-user testing for collecting End-user feedback Identify bottlenecks and points of improvements
BASIC PILOT FINAL RELEASE (KLINK version 1) | DECEMBER 22ND 2014 | Same as Version 0, but with increased resiliency Local search where needed | Consolidating Version 0 w.r.t. End-User feedback and resiliency
ENHANCED PILOT PRELIMINARY RELEASE (KLINK version 2) | FEBRUARY 28TH 2015 | 3 additional institutions Effective presentation Personalization features (only where KLINK Full Installation is possible) Good Resiliency | Extending version 1 w.r.t. more institutions and features Collecting End-User Feedback Identify bottlenecks and points of improvements
ENHANCED PILOT FINAL RELEASE (KLINK version 3) | MARCH 31ST 2015 | Same as version 2 | Consolidating Version 2 w.r.t. End-User feedback

## Slide 6: Software Releases: Tasks 1/2
Emanuele Panzeri
  Role: Developer
  Tasks: Core Component
  Subtasks:
    Capacity Development: provider of requirements for outsourcing not critical core modules development. Workflow: D-Team  Gianluca  D-Team
    GIS oriented extensions: in coordination with Stèphane Hevriod. Workflow: D-Team  Stèphane + Gianluca  D-Team
Alessio Vertemati
  Role: Developer
  Tasks: Adapter Component
  Subtasks
    Capacity Development: provider of requirements for outsourcing not critical adapter modules development. Workflow: D-Team  Gianluca  D-Team
    Information visualization: in coordination with Victor. Workflow: D-Team  Gianluca + Victor  D-Team

## Slide 7: Software Releases: Tasks 2/2
Diego Bernini
  Role: Software Architect
  Tasks: Co-Coordination with Gianluca and Reporting
  Subtasks
    Capacity Development:
    Arrangement of the technical documents to be shared with the parties (Terms of Reference for CA software companies, technical parts of MoU, etc.). Workflow: (D-Team  Gianluca  D-Team)  Gianluca  Parties
    Development Coordination:
    Monitoring the outsourced development (D-Team  Gianluca  D-Team)  Gianluca  Sw House
    Monitoring the compliancy between users’ needs and software features design & development
    Monitoring the information flow and responsible for the deadline respect

## Slide 8: Documentation: deadlines
DOCUMENT | DEADLINE | RATIONALE
GIZ OFFICIAL KLINK ENHANCED PILOT DERIVABLE | NOVEMBER 15TH 2014 | Report describing the performed activities according to the ToR and the technical offer
KLINK BASIC PILOT REPORT | DECEMBER 22ND 2014 | Report describing real Basic Pilot achievements
KLINK ENHANCED PILOT REPORT | MARCH 31ST 2015 | Report describing real Enhanced Pilot achievements
USER MANUAL | MARCH 31ST 2015 | A manual for End-users for easy usage of KLINK
TECHNICAL DOCUMENTATION | Must be always updated according to the development progress | Quick technical documentation for external developers about API provided by the components

## Slide 9: Documentation: tasks for technical reports
Diego: governance of technical reports
  Organization of contents according to ToRs and technical offers
Emanuele & Alessio: providing specific contents related to their components + support for checking technical reports
Victor (Xavi) & Alessandro: providing specific contents related to R&D features (see last part of the presentation)

## Slide 10: Delivery Team Methodology

## Slide 11: Key Methodological Points: overall process
SCRUM as guideline for the software development process
Daily (hopefully) brief meetings among the Delivery Team members (may be 10’-30’ each) for ensuring strong alignment
Each week Diego will provide information about the status of the KLINK Delivery Team activities to Gianluca (and eventually Bernardo too)
  Suggested way: weekly Skype Calls

## Slide 12: Key Methodological Points: documentation
Technical documentation: IEEE standard as guideline when possible
  Delivery Planning: IEEE Std 1058-1998, "Software Project Management Plan (SPMP)"
  Requirements Specification: IEEE Std 830-1998, "Software Requirements Specification (SRS)"
  Architecture and design: IEEE Std 1016-2009 + a specific architectural method (Bernini & Tisato)
  Verification and Validation: IEEE Std 1012-2012
Google Drive for collaborative access and writing of documents
  We will provide access to our shared folder

## Slide 13: Key Methodological Points: development
GIT as version control over a dedicated SIRIS server (Hetzner EX40)
Exploiting Virtual Machines on the Cloud for emulating the target production environments
Continuous testing and deployment over these Virtual Machines
Creation of proper questionnaires for collecting user feedback when versions 0 and 2 will be released

## Slide 14: Beyond the Pilot

## Slide 15: Class of services and tools
K-SEARCH: the Web-based services provided by the K-LINK Pilot focusing on searching contents
K-BOX: a Dropbox-like tool for managing documents in Desktop computers integrated with K-SEARCH

## Slide 16: Proposals for the R&D group
Two proposals for supporting the Enhanced Pilot stage
Effective presentation: spatial visualization of retrieved documents
Toward K-BOX & semantich enrichment: an ontology about Natural Resource Management domain

## Slide 17: Spatial visualization of retrieved documents
Proposal for: Stéphane & Victor (Xavi)
Assume that retrieved documents by a specific query own location labels
Goal: exploiting maps for enriching the standard visualization
Example:
  Coloured regions over a a map indicating the density of referred location labels by the retrieved documents
  Users can see the retrieved documents related to each region

## Slide 18: An ontology for the NRM domain
Proposal for: Alessandro
Define an ontology of NRM domain
Focus on supporting classification and reasoning over produced documents and contents
Goal: a such ontology will be the basis for K-BOX and for building enhanced semantic search services